## Meeting 11-14-2023
Meeting Date | 2023-11-14 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) The city has received a grant fo $30,000 towards the Mayor's Park project to install boat and kayak docks there.
The total cost of this project is $50,000 and the city is going to cover the $20,000 gap. The docks will now be oredered
and hopefully installed in time for use this summer.
2) There will be a meeting about the extension of the bike path down Sweeney Street on Wednesday, Dec. 6th. The meeting
will be held at 500 Wheatfield Street. Committee members will be notified of the time when it is determined. This committee
will also receive an electronic copy of the drawings for the bike path's construction in the near future. Telephone poles
along Sweeney Street are currently be relocated to facilitate the bike path construction.
3) A possible upgrade to the bathrooms at Mayor's Park will be discussed furhter at out next meeting.
4) The Waterfront Revitalization Commission is looking for volunteers to help rewrite and update the cities charter.
The meeting was adjourned @ 7:25 PM
The Waterfront Commission will have their next meeting on Tuesday, January 9th 2024 @ 7:00 PM.

## Meeting 10-10-2023
Meeting Date | 2023-10-10 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) The proposed dock project for Mayor's Park has been bonded by the city and will be implemented in 2024.
If the city receives a future grant for this project that money will be used to pay off the city's bond for this project.
2) The city has started removing some trees along Sweeney St in preparation of extending the bike path from Mayor's Park
to the Botanical Gardens. Some telephone poles have been moved as well. This project is scheduled to take place in 2024.
3) Hydro seeding of the berm at the public parking area has taken place at the bike path extension through Wardell's
boat yard.
Old Business
1) There is no new information concerning the possibility of updating the current bathroom facilities at Mayor's Park.
This committee will make this project one of its focus points for the future.
The meeting was adjourned @ 7:20 PM
The Waterfront Commission will have their next meeting on Tuesday November 14th @ 7:00 PM.

## Meeting 6-21-2023
Meeting Date | 2023-06-21 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 4:30 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) Alex Domardzki met with members of the Waterfront Commission at Mayor's Park to talk about possible improvements
to the park and its facilities.
2) Committee members toured the park and identified several potential projects:
A) The bathroom facilities have not been updated since their installation years ago and could use a facelift. Alex explained
that at some point the park might provide overnight camping to people that were biking or kayaking through the area.
Currently a portable toilet is on location for people's use when the permanent bathrooms are not open.
(see images 1, 2 & 3 below)
B) The kitchen in the main pavilion has basic amenities but seems sufficient for people that reserve this pavilion.
(see image 4)
C) The fence behind the pavilion needs to be painted and Alex informed us that the local scout troop was going to be painting
the fence this summer. On the other side of the fence shoreline erosion is an issue and might be the focus of a future
waterfront project. (fence is pictured in image 5)
D) The area of the park that might be used as a potential camping site was identified by Alex. (see image 6)
Old Business
1) Although the city did not receive a grant to install boat and kayak docks the LCDC might be writing a grant request
to fund this project. It's our understanding the grant awards would be announced near the end of the year. In the
meanwhile the city has started bond solicitations that would separately fund the Mayor's Park dock project. If the city receives
grant money later for this project from the LCDC it could be used to repay the city.
(see image 7 for dock site location)
The meeting was adjourned @ 5:15 PM
The Waterfront Commission will not meet in July or August. The next meeting will take place Tuesday September 12th @ 7:00 PM.
Image #1
Image #2
Image #3
Image #4
Image #7
Image #5
Image #6

## Meeting 5-9-2023
Meeting Date | 2023-05-09 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) The city was not awarded a grant to install boat docks at Mayor's Park. The city might apply for a grant for this project
when New York State announces that it is accepting grant requests in the near future.
2) The common council approved the revised bylaws for the Waterfront Commission. The updated bylaws were also voted on by the
Waterfront Commission members and approved for immediate adoption.
3) The city now has a new grant writer and it was stated that only department heads should be interacting with the grant writer
and not individuals from the different departments.
4) As this Commission has been given the mission to identify possible waterfront projects it is also tasked with helping facilitate
waterfront events. The being said the question was raised as to whether or not this commission should be included in conversations
about canal fest seeing as it takes place on the waterfront and at was at one point cancelled for this year and then suddenly the event
was scheduled to take place again. Further discussion on this subject will take place at our next meeting.
4) Canal Cleanup up had a good response with more than 60 community members volunteering to help out. The volunteers
did a great job cleaning up the shoreline in multiple locations.
5) It was brought to our attention that the bike path extension along Sweeney Street has be postponed until next year.
6) The developer that was working towards meeting requirements to develop the fire tower property on Tonawanda Island has
been released. The city is once again going to solicit bids from developers for the development and sale of this property.
Old Business
1) Improvements/upgrades for the bathrooms at Mayor's Park are still being considered as a future waterfront project.
The Waterfront Commission is planning its next meeting at Mayor's Park to do a site survey to see what might be
the scope of the improvements needed.
The meeting was adjourned @ 7:45 PM
The next meeting will be held in June at a date and time to be determined.

## Meeting 3-14-2023
Meeting Date | 2023-03-14 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) We are presently waiting to see if the city will receive any grant money for the purchase and placement of boat docks
at Mayor's Park. It was stated that we hope to hear about the grant status sometime in May.
2) Emily Root reported on the updated bi-laws that this committee submitted to the Mayor for review. The Mayor made two
minor changes to the proposed bi-laws which the committee reviewed at this meeting and voted to accept. (See the updated bi-laws attached)
The current bi-laws were adopted back in 1992.
3) It was agreed that Steve Pawlick and Craig Greer would present the new bi-laws at the next Common Council meeting to be held
on Tuesday, March 28th at 6:30 PM for approval and adoption.
4) Canal Cleanup is scheduled for Saturday April 22nd from 9:00 -12:00 AM. The city has registered this event with NY State.
Tim Martin and Ed Smolinski are coordinating the cleanup event kicking off at 9:00 AM at the main pavilion at Mayor's Park.
Listed below are the companies that are making donations so far for this event:
1) Galasi's Sub Shop is donating 3 pizzas
2) Hunt Real Estate is donating coffee and donuts
3) Wal-Mart is donating water and juice
The Boys Scouts will be helping out as well as other people that need to complete Community Service hours.
Old Business
1) The committee is still waiting to hear if Niagara Outfitters might be requesting permits for kayak locker placement
and/or operating kayak rentals at any North Tonawanda park locations.
2) There might be a requirement to put the kayak rentals out for public bid.
3) The committee is still looking at upgrading the bathroom facilities at Mayor's Park for its next project.
The meeting was adjourned @ 7:25 PM
The next meeting will be held on April 11th, 2023 @ 7:00 PM

## Meeting 1-10-2023
Meeting Date | 2023-01-10 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) Jeff Licht, Craig Greer, Ben Meyer and Steve Pawlik have been re-appointed for another two year term beginning January 1, 2023.
The committee agreed to keep Steve Pawlik as Chairman and Craig Greer as Secretary.
2) Emily Root fleshed out a template to use as a guideline for updating the Waterfront Commission's Bi-laws. The commission reviewed
the template and agreed unanimously to accept the bi-law proposal with one minor edit. The commission also agreed to present
the bi-law draft to the Mayor for his review. If accepted by the mayor the draft would be presented to the Common Council for
their approval and future implementation. Emily Root agreed to present the draft to the mayor.
3) Emily asked Alex Domaradzki if he could attend one of our meetings and he said he wouldn't be able to make a meeting on a
Tuesday night. After polling committee members it was agreed to see if Alex could make a meeting on Monday February 13th
@ 4:00 PM. Alex has replied and said that he could make a meeting at that time on the 13th and offered his office as the meeting place
located at 500 Wheatfield Street. The committee members agreed to that time and location.
4) The committee discussed ideas for possible new future projects. Possibly upgrading the bathrooms at Mayor's Park was entertained
as a possibility as they are a bit outdated. If the funding for the new boat docks at Mayor's Park is approved this project would go
hand in hand creating a positive experience for users. Further discussions will take place at the next meeting.
Old Business
1) The committee is still waiting to hear what Niagara Outfitters might be requesting permits for in reference to kayak locker placement
and/or operating kayak rentals at any North Tonawanda park locations.
The meeting was adjourned @ 7:40 PM

## Meeting 12-13-2022
Meeting Date | 2022-11-15 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Tim Martin |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
Mayor Austin Tylec attended this month's meeting and shared some information with the committee.
1) Mayor Tylec stated that the outdated By-Laws for this committee needed to be updated. The current By-laws
can be viewed below. Emily Root volunteered to check with other Waterfront Commissions to see if their By-laws
could be used as a possible template to update our own By-laws. Any By-law updates will need to be approved by the
common council.
2) At this point the city is not sure if Libby from Niagara Outfitters is going to again apply for a permit to offer kayak rentals
and or a possible kayak locker system for the Botanical Gardens site or for the possible future site of a kayak launch
at the proposed Mayor's Park site.
3) Currently the city is waiting to see if it is awarded any funds through the DRI grant awarding process which might be
announced any day. Other state awarded grants may not be announced until May of 2023. |  |  | DRI Projects Approved
4) Adam Domardzki has applied for a grant for purchasing and installing the boat and kayak docks at Mayor's Park.
5) It was requested that Donna Braun and Alex Domardzki have their emails added to the disbursement list for the minutes
from the Waterfront Committee meetings. This has been done as requested.
Next meeting to be held on Tuesday January 10th @ 7:00PM
The meeting was adjourned @ 7:35 PM
Waterfront Commission By-laws
1. The Waterfront Commission will act as an advisory board to the Mayor.
2. All Waterfront Commission members will be appointed by the Mayor.
3. The Waterfront Commission will consist of twelve (12) members and a chairman.
4. Terms will be for two years.
5. The Waterfront Commission will have at least six (6) meetings a year.
6. The Waterfront Commission will have a secretary, appointed by the Mayor, who
receive a stipend to prepare minutes and send out mailings.
7. The Waterfront Commission will deal with issues involving the Erie Canal, Niagara
River, all connecting, related waterways and land adjacent to said waterways.
8. A quorum is needed to conduct business and vote on issues.
9. Three (3) unexcused, consecutive absences are ground for removal from the
Waterfront Commission.

## Meeting 11-15-2022
Meeting Date | 2022-11-15 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Craig Greer |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) Emily Root called Dave Conti so he could share with our committee the priorities and project goals for the Botanical Gardens
A) Top priority is obtaining funding mainly via grants for their three phase project initiative
1) Phase one - Entrance and parking lot renovation
2) Phase two - Greenhouse and garage renovation, build meeting room, atrium, small kitchen and two story butterfly conservatory
3) Phase three - Site renovation
See artist renderings of these projects below…
2) The question was raised as to what smaller projects might be aligned with the Waterfront Committee goals? It was suggested that this
committee might be able help in the effort to obtain funding/grants for the purposes listed below:
1) Watershed training / Water testing
2) Gross Out Camp (Science based summer camp)
3) Additional plantings
4) Other educational programs
5) Stipends for volunteers
6) Transportation for programs
7) Rental Equipment for functions/programs
8) Lunches for function/programs
3) Dave Conti said small grants in the neighborhood of $50 thousand dollars might be possible through East Hill, Wal-Mart or Ralph Wilson Jr. foundations.
Emily Root volunteered to act as liaison between the Botanical Gardens and the Waterfront Committee to keep us updated. It was suggested that
perhaps the Waterfront Committee could monitor grant requests to avoid different city departments competing for the same grants which has
apparently happened in the past. It was also stated that the city needed to update the LWRP (see LWRP image) to reflect future projects under consideration
including the Botanical Garden projects listed above. It was suggested that we talk to city planning board as well as the mayor to inquire
about any other pending or future projects that might also be looking for funding. The committee needs to understand how the whole process
for funding is supposed to work so it can be done efficiently and effectively. Tim Martin and Emily Root plan to meet with the Mayor to possibly
set up a process for funneling projects pertaining to the waterfront through this committee.
4) It was mentioned that Niagara Outfitters have requested permission to run kayak tours out of Mayor's Park as well as possibly place kayak lockers
here to store kayaks. We are looking for more information about this request.
Project Update
1) Containers for depositing used fishing line have been installed at the fishing platform at the foot of Niagara Street
Next meeting to be held on Tuesday December 13th, 2022 @ 7:00PM
The meeting was adjourned @ 8:15 PM

## Meeting 10-11-2022
October 11th, 2022, 7pm at City Hall
Present: Justin, Tim, Emily, Larry, Jeff
Debrief from Steve and Tim’s meeting with Mayor Tylec and Laura Wilson from Lunber City Development Corporation:
· Reiterated the importance of the city’s Local Waterfront Revitalization Plan (LWRP) and Comprehensive Plan, which serve as the blueprint for waterfront development. The Commission members should familiarize themselves with these documents in order to understand what has been identified as priority actions for the waterfront, and determine how we can help drive these forward. Both documents can be found in this dropbox folder-https://drive.google.com/drive/folders/1eG2nuRUOLO1WkebIVxc9A9rJo0ZqUfW5
· In general, we should think of additional work or projects we want to advance or be involved in, in addition to the Mayor’s Park dock project.
· As long as things are inside LWRP zone, we can apply for state funding to support projects.
· Looking primarily at state funding for the dock at Mayors Park. No city funds are currently available.
· We should revisit the list of projects we started earlier this year, and prioritize additional work we want to move forward.
· Sweeney St Bike Path:There’s a committee for putting the bike path along Sweeney Street, we could be more involved with that.
Discussion:
· Will state funding require us to do feasibility studies and engineering? After the meeting with the Mayor, Alex from the Parks Department reached out to Emily R and Laura Wilson to discuss potential options for funding of the Mayors Park dock in addition to state funding. Some options are Wilson Funding, up to $50k, due early November. Also potentially East Hill Foundation, Canal Corps, and Greenway funds.
· Sweeney St Bike Path:How far along is the project? They were on hold b/ of lack of funding but may be starting up again soon. Potentially implementation of the bike path in 2023.
· Discussed the WC having more authority for waterfront projects in NT.
· Discussed WC bylaws from around 1990. Act as advisory board to mayor, consist of 12 members and chairman (could add more members), 2 year terms, at least 6 mtgs/year, etc.
· Talked about revisiting other project ideas-
· Priority for projects $50k or more, so we can go for Wilson Foundation and other similar funding
· Property that city owns on Tonawanda island, where old fire tower is. Yacht club has docks on that side of the island that they remove in winter. Are there plans for development here? If not, there is lots of opportunity there for improvement
· Any brownfield properties along waterfront? Can we make those more visually pleasing. Thinking of the area along the river where new bike path improvements were recently made, are there opportunities adjacent to that to clean things up?
· Focus on city owned properties
· Talked about North Tonawanda Botanical Gardens- contamination issues which prevent the implementation of more shoreline restoration in other areas of the property. What improvements could be made to the greenhouse?
o Emily to talk to NTBGO about what we can do to help move their priorities forward in the next 5 years. Hopefully have someone come talk to the Committee at an upcoming meeting.
· Mayors Park- do the bathrooms need renovations?
Action Item: Before the next meeting, all Committee members should look at relevant sections of the LWRP (linked above), think of priority ideas for projects we want to move forward and come with ideas next meeting with ideas to discuss. These ideas could be existing projects identified in the LWRP, or new ideas. If you can’t make it to the next meeting, send project ideas to group via email, or add them to the document linked below.
The list of project ideas we started earlier this year can be found here-Waterfront Commission Project List.xlsx Everyone should be able to edit it. Feel free to add project ideas to the spreadsheet.
Meeting adjourned at 7:55

## Meeting 9-13-2022
Meeting Date | 2022-09-13 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) Steve Pawlick talked to Alex Domardzki about the proposal of placing boat docks at Mayor's Park and he was in favor of the idea. Alex did
raise the concern that from a safety stand point that perhaps it would be smart to have safety railings on the walkway out to the docks.
The committee agreed.
2) Alex also stated that his department was researching the possibility of placing a kayak launch at Gateway Park.
3) It was reported that funding for the Mayor's Park boat dock proposal may not be available until next year. Emily Root volunteered to
research other possible avenues of funding for this proposal. Lumber City Development might be a possible source.
Old Business:
1) We received clarification from questions raised at the last meeting about when the bathrooms at the city parks were supposed to be
open for public use. For Gratwick Park the bathrooms should be open the same hours the park is open and every day that the park is open.
For all other parks the bathrooms are open only when the pavilions in those parks have been reserved. The bathrooms at Gateway Park
are open the same hours that the dock hands are scheduled to work. The bathrooms at Lumber Jacks Marina are only available to boaters
who are paying for slip rental. Those renters are given a code to access the bathrooms there.
Other Business:
1) It appears that the extension of the bike path adjacent to Wardell's Boat Yard has been completed along with the placement of rocks
to separate the bikers and walkers from the traffic through the boat yard. The existing bike bath was also repaved all the way to Gratwick Park.
It is believed that there is still some signage to be placed identifying the path near the Key Bank on River Rd.
2) It was noted that the property across the street from Gateway Park that was previously occupied by Pierson Auto Parts was being prepped
for new construction.
Next meeting to be held on Tuesday October 11th, 2022 @ 7:00PM
The meeting was adjourned @ 7:40 PM

## Meeting 8-9-2022
Meeting Date | 2022-08-09 | Members in Attendance
|  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) Everyone agreed on the Mayor's Park dock installation proposal that we received from Anchor Marine. Emily Root did an
excellent job of putting the proposal into a summary that the committee unanimously approved.
2) The committee approved sending the summary to all appropriate parties. Emily volunteered to send the summary out
as well as sending out a follow up email to make sure that the approval process does not get stalled out at some point along the line.
Old Business:
1) Question were again raised about the portable bathrooms at Gratwisk Park which also developed into a discussion about the bathrooms at Mayor's Park.
It seems the bathrooms at Gratwick Park were locked during the boat races and other public events. When the bathrooms were open on a different
occasion only one of the stalls were open and that bathroom had a broken toilet seat. The schedule and criteria for having the bathrooms at both parks was
brought into question and the committee agreed to looking into those details.
2) The Bicycle Path Extension has seen contractors grinding and prepping the current path from Gratwick Park to Wardell's boat yard
it is believed that paving should start shortly along with adding the new section that will connect our bike path to the river walk.
Other Business:
1) No other business
Next meeting to be held on Tuesday September 13th, 2022 @ 7:00PM
The meeting was adjourned @ 7:40 PM

## Meeting 4-12-2022
Meeting Date |  | 2022-04-12 | Members in Attendance
|  |  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  |  | Emily Root | Ben Meyer
by Steve Pawlick |  |  | Joseph Petrie | Larry Young
|  |  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) The minutes for the March 8th, 2022 meeting were accepted as read by the committee.
2) Guest speaker for this meeting was City Engineer Chelsea Spahr and she gave us a briefing on the status of several projects for the city such as:
A) | The bike path connector construction has begun that will connect the current bike path that ends near the Key Bank on River Rd to the
Tonawanda bike path. Land along the River Rd bridge berm is being cleared and a parking area for people that are using the new bike path
is being prepared. The bike path connector will travel parallel to the Wardell Boat yard and under the River Rd. bridge via the foot of Sweeney St.
The bike path will then travel up the South side of Sweeney St as it crosses Manhattan St. and parallel to the current Suzuki Strings building.
When the bike bath meets Webster St it will make a right hand turn and cross the bridge into Tonawanda where it will connect with their bike path.
The current bike path will be repaved from Key Bank at River Rd and Goundry St all the way out to Gratwick Park as it makes its final link to the
newly built connector. Permits are still pending for the work that will be done on the state property. The current target date for completion of
this project is from mid July to mid August 2022.
B) | The bike path extension from Mayor's Park to the Botanical Gardens has a current target completion date of Spring 2023. This extension will be
8 to 10 feet wide and will run along the south side of Sweeney St as opposed to running along the edge of the canal on private property.
The bike path will saw cut through any driveways it encounters along the way. Currently there are some storm sewer issues that are being abated
as well as some line of travel issue where there is limited free space to place the bike path.
C) | The portable 9 unit bathroom facility is currently located at Gratwick Park for the summer and is having a hard connection to city water installed.
The facility is currently having its pump out schedule reviewed to ensure it is functioning properly during times of heavy usage as the unit is
self contained and can not be connected to the cities sewer system.
D) | The fire tower property that the Penrose Company wants to develop has triggered an infra structure review to insure that utilities on Tonawanda Island
where it is located can handle the potential increased demand for water, sewer and power needs.
E) | The installation of new water lines on the city boathouse property is still awaiting a right of way approval to cross private property. As of this meeting
there has been no funding allocated for this project where the city was going to make the initial investment for the installation and then be reimbursed
via special assessment to the lease holders over the next five years. Ms. Spahr said that no project plan is currently being developed to complete this task
that she is aware of.
2) The committee decided to prioritize and focus on one project that they felt they could complete and after some discussion all attendees agreed to work
towards installing some boat docks at Mayor's Park to allow access to the park from the water. Currently there is already a cement structure there that could
possibly be utilized to anchor a floating dock system. It was also mentioned that possible the City of Tonawanda had some floating docks that they no longer needed
and that might be a possible resource that would defray the costs of this project. Committee members agreed that we all needed to know about the process
of requesting grant money to fund city projects and wanted to extend an invitation for the city grant writer to attend our next meeting to share some information.
3) The committee would also like to invite Mayor Austin Tylec to their next meeting to discuss goals and the process to achieve those goals.
Old Business:
1) Canal cleanup is scheduled for Saturday April 23rd, 2022 from 9:00-12:00. The required application for this activity has been accepted by New York State.
Areas targeted are the canal shoreline from Vandervoort Street and Sweeney St. to the Service drive boat launch as well as the shoreline
at Mayor's Park. According to Tim Miller, all action items listed here have been abated and the Canal Cleanup is ready to take place as scheduled.
2) Ed Smolinski has coordinated the following action items:
a) The bathrooms at Mayors Park will be open on the day scheduled for the cleanup
b) Drinking water will be supplied as well as lunch for cleanup participants
c) Gloves, rakes and garbage bags will be supplied as well as some heavy equipment support from the Public Works Dept.
d) Hunt real estate will again donate coffee and donuts for the cleanup kick off that morning
e) Advertising for the cleanup on Face book Community Page & other vehicles for local communication has been coordinated
f) Someone will be designated to be available to sign off on Community Service validation sheets
Other Business:
Next meeting to be held on May 10th, 2022 @ 7:00PM
The meeting was adjourned @ 8:00 PM

## Meeting 3-8-2022
Meeting Date |  | 2022-03-08 | Members in Attendance
|  |  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  |  | Emily Root | Ben Meyer
|  |  | Joseph Petrie | Larry Young
|  |  | Jeff Licht | Tim Martin
(Red = Absent)
New Business:
1) Committee members reviewed the updated Statement of Purpose and accepted it unanimously. Emily Root agreed to send the
updated document to Austin Tylec and Angela Johnson. The statement will also be added to North Tonawanda website under the Waterfront Committee link.
2) The committee members submitted project ideas for discussion and Emily Root agreed to enter them into the North Tonawanda LWRP in order to make
it a more current and viable document.
3) Annually the Waterfront Committee has taken a tour of the city's waterfront from the water for a better perspective of the waterfront property that the
city manages. It was agreed that this review would be scheduled for June of 2022.
4) In an effort for the committee to become more informed about what might be involved in future projects as well as the status of some pending projects it was
decided that we should invite guests to our future meetings that could share information from their area of expertise. It was agreed to invite
City Engineer Chelsea Spahr to our next meeting if she was available. Other guests for future meetings include someone from the Canal Corporation,
Lumber City Development Corporation and the Director of the North Tonawanda Recreation Department.
Old Business:
1) Canal cleanup is scheduled for Saturday April 23rd, 2022 from 9:00-12:00. The required application for this activity has been accepted by New York State.
Areas targeted are the canal shoreline from Vandervoort Street and Sweeney St. to the Service drive boat launch as well as the shoreline
at Mayor's Park.
2) Ed Smolinski has coordinated the following action items:
a) The bathrooms at Mayors Park will be open on the day scheduled for the cleanup
b) Drinking water will be supplied as well as lunch for cleanup participants
c) Gloves, rakes and garbage bags will be supplied as well as some heavy equipment support from the Public Works Dept.
d) Hunt real estate will again donate coffee and donuts for the cleanup kick off that morning
e) Advertising for the cleanup on Face book Community Page & other vehicles for local communication has been coordinated
f) Someone will be designated to be available to sign off on Community Service validation sheets
Other Business:
Next meeting to be held on April 12, 2022 @ 7:00PM
The meeting was adjourned @8:15 PM

## Meeting 2-8-2022
Meeting Date |  | 2022-02-08 | Members in Attendance
|  |  | Steve Pawlick | Craig Greer
Meeting called to order @ 7:00 PM |  |  | Emily Root | Ben Meyer
|  |  | Joseph Petrie | Larry Young
|  |  | Jeff Licht | Tim Martin
(Absent due to Quarantine)
New Business:
1) The minutes from the January 11, 2022 meeting were read and Emily Root made a motion to accept the minutes as read, Steve Pawlick seconded the motion.
2) Larry Young was introduced as new member and his contact information was collected for Waterfront Committee Info Sheet
3) Guest speaker Errick Zadzilka gave the committee an update on the Botanical Gardens project (See attachments in this email)
Errick explained the importance of updating N. Tonawanda's Local Waterfront Revitalization Plan (LWRP) as a current LWRP is a critical element
required for future grant considerations. Emily Root said she would send committee members a copy of our current LWRP for review and suggestions
for its update. As these minutes were being typed I received a link from Emily for the city's LWRP as well as other cities updated LWRPs that
could be used as a possible guideline for our own. It was also questioned as to whether or not we needed any funding to update our LWRP and what
new waterfront projects might be considered in that update.
4) The committee also discussed that in conjunction with the Botanical Gardens project if we should consider adding amenities for mooring boats
at the Botanical Gardens to allow access from the water for people that wanted to visit the Botanical Gardens
5) It was stated that the Waterfront Committee will be added to the city website which could be used to keep the community up to date on its
projects as well as a possible communication tool for community input.
Old Business:
1) Canal cleanup is now scheduled for Saturday April 23rd, 2022 from 9:00-12:00. The required application for this activity has been accepted by New York State.
Areas targeted are the canal shoreline from Vandervoort Street and Sweeney St. to the Service drive boat launch as well as the shoreline
at Mayor's Park.
2) Ed Smolinski has agreed to coordinate the cleanup activities and either complete or delegate these action items:
a) Make sure the bathrooms at Mayors Park are open on the day scheduled for the cleanup
b) Contact Wal-Mart or local business for drinking water donation
c) Inquire to see if the Mayor's Office will again supply some type of lunch for cleanup participants
d) Inquire to see if Hunt real estate will again donate coffee and donuts for the cleanup kick off that morning
e) Advertise the cleanup on Face book Community page or other vehicles for local communication
Other Business:
The Waterfront Committee is still waiting for updates on the following:
1) Status of the River Walk extension from the River Road Key Bank through property adjacent to Wardell's boatyard
2) Status of condos being constructed on Tonawanda Island
3) Status of the ROI (Return On Investment) of Lumber Jakes Patio Grill and Marina
4) Status bathrooms at Gratwick Park
Next meeting to be held on March 8, 2022 @ 7:00PM
A motion to adjourn was made by Steve Pawlick and seconded by Larry Young.

## Meeting 1-11-2022
Meeting Date |  | 2022-01-11
Meeting called to order @ 7:00 PM
New Business:
1) It was quickly discovered that the chairman of this committee was not re-appointed after his term ended recently.
Steve Pawlik was the senior member of this committee and agreed to act as chairman until other arrangements could be made.
Craig Greer agreed to take the minutes for the meetings.
2) Three new members introduced themselves as:
Emily Root
Joseph Petrie
Tim Martin
Old Business:
In order to bring new members up to date there was a short discussion about past and pending projects such as:
1) Procurement and placement of kayak docks.
2) Bathrooms housed in trailers for Gratwick Park (Mentioned that the committee would like an update on this project)
Potential New Projects Discussed:
1) Canal Cleanup (Tim Martin to contact Ed Smolinski to help coordinate as he had acted in that capacity in the past)
2) Possibilities for areas to be identified for potential shoreline restoration. Emily Root talked about the initiatives undertaken
by Buffalo Niagara Waterkeeper group.
3) Possible procurement and placement of boat docks at Mayor's park to expand accessibility
4) Cleanup of area across the street from the Remington Tap Room on canal side. Committee was inquiring as to who was responsible
for maintaining this area as it was overgrown with weeds.
5) Possibility of adding decorative lights to the Webster Street Bridge to enhance canal experience.
6) Possibility of expanding parking at Service Drive boat docks.
Other Business:
It was discussed that it would be nice if this committee could be kept in the loop as far as city projects concerning the waterfront.
Committee members are often asked by residents of North Tonawanda about the projects that have heard about and it would
be nice if the committee members could answer those questions intelligently to the extent possible. Some of the projects that
this committee would like updates on are:
1) Status of the River Walk extension from the River Road Key Bank through property adjacent to Wardell's boatyard
2) Status of condos being constructed on Tonawanda Island
3) Status of the ROI (Return On Investment) of Lumber Jakes Patio Grill and Marina
4) Status bathrooms at Gratwick Park
Next meeting to be hel on Febuary 8, 2022 @ 7:00PM
Meeting was adjourned by Chairman Steve Pawlick at 8:00 PM

## Sign in Sheet
Waterfront Commission Sign In Sheet
Meeting Date: August 9th, 2022
Name | Email | Phone # | Signature
Emily Root | emily.kate.root@gmail.com | 240-643-6036
Joseph Petrie | josephpetrie95@gmail.com | 716-550-3333
Ben Meyer | benjamenlmeyer@gmail.com | 716-696-2573
Tim Martin | martintim055@gmail.com | 716-863-5515
Jeff Licht | jlicht7048@aol.com | 716-628-0693
Craig Greer | cgreer51@aol.com | 803-243-5713
Steve Pawlik | pawlik1100@verizon.net | 716-432-9877
Larry Young | lry15@roadrunner.com | 716-440-6606

## Mermber Info Sheet
Waterfront Commission Member Information
Name | Email | Phone #
Emily Root | emily.kate.root@gmail.com | 240-643-6036
Joseph Petrie | josephpetrie95@gmail.com | 716-550-3333
Ben Meyer | benjamenlmeyer@gmail.com | 716-696-2573
Tim Martin | martintim055@gmail.com | 716-863-5515
Jeff Licht | jlicht7048@aol.com | 716-628-0693
Craig Greer | cgreer51@aol.com | 803-243-5713
Steve Pawlik | pawlik1100@verizon.net | 716-432-9877
Larry Young | Lry15@roadrunner.com | 716-440-6606